## 4.3
| BOQ |  |  |  | BUDGET |  |  |  | PLANNED/ACTUAL BREAKDOWN | [12 empty] | Sum
| Item | QTY hr or tons | U Cost qr/h-ton | orgnl budg qr | Rev1 budg qr | Rev2 budg qr | Rev3 budg qr | % | 2017-12-17 | 2018-01-01 | 2018-02-01 | 2018-03-01 | 2018-04-01 | 2018-05-01 | 2018-06-01 | 2018-07-01 | 2018-08-01 | 2018-09-01 | 2018-10-01 | 2018-11-01 | 2018-12-01 | Total |  | Remaining
1 | Manpower
| Production (70 h/t) | 86520 | 5 | 111280 | 2022324 | 2732160 | 2810160 | 6.076% | -222324 | -10405.1429 | -10405.1429 | -10405.1429 | -10405.1429 | -10405.1429 | -10405.1429 | -10405.1429 | -10405.1429 | -10405.1429 |  |  |  | -315970.2857 | EAC | 2565160.4943
|  | hrs | [6 empty] | -2143601.22 | -24699.84 | -50439.34 | -45081.8 | -90083 | -47982 | -101163.42 | -140827.99 | -157234.45 | -29723.31 | -5845.63 | -44448.78 |  | -2881130.78 | AC
| Engineering (3 h/t) | 3708 | 50 | 18400 | 840000 | 1036000 | 1101000 | 2.524% | -840000 | -28000 | -28000 | -28000 | -28000 | -28000 | -28000 | -28000 | -30689.2514 | -30689.2514 | -6000 |  |  | -1103378.5029 | EAC | 41804.5071
|  | hrs | [6 empty] | -829790.54 | -34850.93 | -32071.78 | -24240.6 | -31396.9 | -37596.5 | -23683.45 | -16719.89 | -37635.36 | -35666.07 | -21081.94 | -20449.05 |  | -1145183.01 | AC
| Projects (7 h/t) | 8652 | 50 | 432600 | 1260000 | 1456555 | 1502555 | 3.785% | -110450 | -7479.9164 | -7479.9164 | -7479.9164 | -7479.9164 | -7479.9164 | -7479.9164 | -7479.9164 | -32000 | -32000 | -32000 | -32000 | -32000 | -322809.4147 | Plan | 1075934.2653
|  | hrs | [6 empty] | -1041204.36 | -53635.33 | -57308.09 | 63664.4 | -61681 | -34942.6 | -50009.04 | -32792.54 | -53440.16 | -37274.1 | -9504.76 | -30616.1 |  | -1398743.68 | Actual
| Construction/Site (60 h/t) | 74160 | 14 | 1038240 | 760000 | 1278309 | 1805309 | 2.283% | -620000 | -50000 | -75000 | -70000 | -85000 | -83400 | -90000 | -90000 | -80000 | -30000 | -150000 | -150000 | 0 | -1573400 | Plan | 211549.16
|  | hrs | [6 empty] | -617417.51 | -55458.64 | -81118.02 | -91151.2 | -100895.8 | -80410.6 | -135317.68 | -88852.19 | -175921.3 | -174931.95 | -107946.4 | -75527.87 |  | -1784949.16 | Actual
| QHSE (4 h/t) | 4944 | 50 | 24700 | 520000 | 550000 | 715000 | 1.562% | -500000 | -37631.841 | -37631.841 | -37631.841 | -37631.841 | -37631.841 | -37631.841 | -37631.841 | -30000 | -25000 | -5000 | -5000 | 0 | -828422.8867 | Plan | -125089.2267
|  | hrs | [6 empty] | -477787.26 | -16127.93 | -22120.11 | 21822.4 | -29314.5 | -25395 | -27043.23 | -31574.36 | -32762.15 | -20145.44 | -16209.35 | -26676.73 |  | -703333.66 | Actual
| Total Plan | 177984 |  | 1625220 | 5402324 | 7053024 | 7934024 | 16.23% | -2292774 | -133516.9002 | -158516.9002 | -153516.9002 | -168516.9002 | -166916.9002 | -173516.9002 | -173516.9002 | -183094.3943 | -128094.3943 | -193000 | -187000 | -32000 | -4143981.0899 | Plan | 3769359.2001
| Total Actual | [7 empty] | -5109800.89 | -184772.67 | -243057.34 | -74986.8 | -313371.2 | -226326.7 | -337216.82 | -310766.97 | -456993.42 | -297740.87 | -160588.08 | -197718.53 | 0 | -7913340.29 | Actual
| Accum Total Plan | 177984 |  | 1625220 | 5402324 | 7053024 | 7934024 | 16.23% | -2292774 | -5243317.7902 | -5401834.6904 | -5555351.5906 | -5723868.4907 | -5890785.3909 | -6064302.2911 | -6237819.1913 | -6420913.5856 | -6549007.9799 | -6742007.9799 | -6929007.9799 | -6961007.9799 | -6961007.9799 | Plan | 952332.3101
| Accum Total Actual | [7 empty] | -5109800.89 | -5294573.56 | -5537630.9 | -5612617.7 | -5925988.9 | -6152315.6 | -6489532.42 | -6800299.39 | -7257292.81 | -7555033.68 | -7715621.76 | -7913340.29 | -7913340.29 | -7913340.29 | Actual
2 | Material
| Steel SectionA ton | 723.06 | 2700 | 1952262 | 2300000 | 2366558 | 2148197 | 6.91% | -2105000 | -5000 | -5000 | -10000 | -10000 | -10000 | -10000 | -10000 | -10000 |  |  |  |  | -2175000 | Plan | 191558
[9 empty] | -2077301.6346 | -1893.6 | -10515 | -1997 | -11120.5 |  | -26784.06 | -1634.4 | -18844.24 | 0 | 0 | 0 |  | -2150090.4346 | Actual
| Steel SectionB ton | 426.42 | 2900 | 123618 | 1100000 | 962307 | 916522 | 3.305% | -700000 | -90343.8691 | -30000 | -30000 | -30000 | -30000 | -30000 | -30000 | -30000 |  |  |  |  | -1000343.8692 | Plan | -38036.8692
[9 empty] | -694554.7851 | -53787.6 |  | -2246 |  | -51300 | -128533.24 | -40780.18 |  | -5135.19 | -3289.5 | 0 |  | -979626.4951 | Actual
| Steel Plates ton | 134.4 | 2400 | 322560 | 585000 | 1056054 | 589467 | 1.758% | 2017-12-17: -585000; 2018-01-01: -10308.838; 2018-02-01: -10308.838; 2018-03-01: -10308.838; 2018-04-01: -8173.838; 2018-05-01: -6008.838 | -630109.19 | Plan | 425944.81
[9 empty] | -533455.81 | -3709.62 |  |  | -16170 | -1691 | -18039.57 | -6005 | -7954.3 | -5685 | -31467.98 | 143862.24 |  | -480316.04 | Actual
| Studs m2 | 8394 | 60 | 503640 | 446000 | 489521 | 516609 | 1.34% | 2017-12-17: -446000; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: -53882.8825; 2018-08-01: -30000 | -529882.8825 | Plan | -40361.8825
[9 empty] | 2017-12-17: -431063.06; 2018-06-01: -32000; 2018-10-01: 0; 2018-11-01: 0 | -463063.06 | Actual
| Light Items | 17400 | 60 | 1044000 | 280000 | 362500 | 361548 | 0.8412% | 2017-12-17: 0; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: 0; 2018-04-01: 0; 2018-08-01: -396000 | -396000 | Plan | -33500
[9 empty] | -25637.79 |  |  |  |  | 0 | 0 | 0 | 0 | -137515.25 | -136876.14 | -74130.48 |  | -374159.66 | Actual
| Wood Items ton | 30 | 4200 | 126000 | 126000 | 218000 | 116982 | 0.3785% | 2017-12-17: -126000; 2018-01-01: -1473.35; 2018-02-01: -1473.35; 2018-03-01: -8064.4917; 2018-04-01: -8064.4917; 2018-05-01: -8064.4917; 2018-06-01: 0 | -128946.7 | Plan | 89053.3
[9 empty] | -101806.525 | 0 | -15175 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | -116981.525 | Actual
| Painting Primer m2 | 25000 | 30 | 750000 | 160000 | 160000 | 121611 | 0.4807% | 2017-12-17: -160000; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: 0; 2018-04-01: -5674.3683; 2018-05-01: 0; 2018-06-01: 0 | -160000 | Plan | 0
[9 empty] | 2017-12-17: -48880.63; 2018-03-01: -8000; 2018-05-01: -38150; 2018-06-01: -25260; 2018-09-01: -1320; 2018-10-01: 0; 2018-11-01: -600 | -122210.63 | Actual
| Fasteners ton | 1236 | 300 | 370800 | 400000 | 530000 | 420103 | 1.202% | 2017-12-17: -400000; 2018-01-01: -18653.1733; 2018-02-01: -21325; 2018-03-01: -14705.9423; 2018-04-01: -14705.9423; 2018-05-01: 0 | -469390.058 | Plan | 60609.942
[9 empty] | -344040.48 | -8015.25 | -29350 | -6120 |  |  |  | -8063 | -10801 | -19963.04 | -5853.12 | 0 |  | -432205.89 | Actual
| Consumables ton | 1236 | 250 | 39000 | 600000 | 630000 | 650601 | 1.803% | 2017-12-17: -600000; 2018-01-01: 13737.9657; 2018-02-01: -13089.4022; 2018-03-01: -13089.4022; 2018-04-01: 0; 2018-05-01: -2600 | -615040.8386 | Plan | 14959.1614
[9 empty] | -449510.4 | -1513 |  | -25355 | -7845 |  | -45028.2 | -18363.48 | -11631 | 0 | 0 | -4344.5 |  | -563590.58 | Actual
| Furnitures | 1 | 150000 | 150000 | 100000 | 100000 | 46000 | 0.3004% | 2017-12-17: 0; 2018-01-01: 0; 2018-02-01: 0; 2018-03-01: -100000; 2018-04-01: 0; 2018-05-01: -64407.5 | -164407.5 | Plan | -64407.5
[9 empty] | 2017-12-17: 0; 2018-09-01: 0; 2018-11-01: 0 | 0 | Actual
| Total Plan |  |  | 5381880 | 6097000 | 6874940 | 5887640 | 18.32% | -5122000 | -112041.2647 | -81196.5902 | -240051.5566 | -76618.6403 | -121080.8297 | -40000 | -40000 | -466000 | 0 | 0 | 0 | 0 | -6298988.8815 | Plan | 575951.1185
| Total Actual | [7 empty] | -4706251.1147 | -68919.07 | -55040 | -43718 | -35135.5 | -91141 | -275645.07 | -74846.06 | -49230.54 | -169618.48 | -177486.74 | 64787.26 | 0 | -5682244.3147 | Actual
| Accum Total Plan |  |  | 5381880 | 6097000 | 6874940 | 5887640 | 18.32% | -5122000 | -5234041.2647 | -5315237.8549 | -5555289.4115 | -5631908.0519 | -5752988.8815 | -5792988.8815 | -5832988.8815 | -6298988.8815 | -6298988.8815 | -6298988.8815 | -6298988.8815 | -6298988.8815 | -6298988.8815 | Plan | -616744.5668
| Accum Total Actual | [7 empty] | -4706251.1147 | -4775170.1847 | -4830210.1847 | -4873928.1847 | -4909063.6847 | -5000204.6847 | -5275849.7547 | -5350695.8147 | -5399926.3547 | -5569544.8347 | -5747031.5747 | -5682244.3147 | -5682244.3147 | -5682244.3147 | Actual
3 | Subcontractor
| Designer | 1236 | 200 | 247200 | 145000 | 145000 | 102000 | 0.4356% | 2017-12-17: -81000; 2018-01-01: -60000 | -141000 | Plan | 4000
[9 empty] | 2017-12-17: -81307.91; 2018-01-01: -1266.67; 2018-03-01: -3167; 2018-04-01: -16000; 2018-10-01: 0; 2018-11-01: 0 | -101741.58 | Actual
| Engineering Shop Drawing | 1236 | 90 | 111240 | 111240 | 175000 | 175000 | 0.3342% | 2017-12-17: -107000; 2018-01-01: -34990.23; 2018-02-01: -34990.23 | -176980.46 | Plan | -1980.46
[9 empty] | 2017-12-17: -106587.27; 2018-01-01: 0; 2018-02-01: -20250; 2018-08-01: -21420; 2018-10-01: 0; 2018-11-01: -4380 | -152637.27 | Actual
| Fire proofing A m2 | 14327 | 55 | 787985 | 533000 | 533000 | 533000 | 1.601% | -70694 | -76636.7133 | -76636.7133 | -76636.7133 | -76636.7133 | -76636.7133 | -76636.7133 | -76636.7133 | -226636.7133 | -76636.7133 |  |  |  | -910424.42 | Plan | -377424.42
[9 empty] | 2017-12-17: -70694.1; 2018-01-01: 0; 2018-02-01: -70694.1; 2018-05-01: -586; 2018-10-01: 0; 2018-11-01: 11382.01 | -130592.19 | Actual
| Fire proofing B m2 | 1398 | 200 | 279600 | 150000 | 150000 | 152000 | 0.4507% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | -30000 | -120408.42 |  |  |  |  | -150408.42 | Plan | -408.42
[9 empty] | 2017-12-17: 0; 2018-01-01: 0; 2018-05-01: -4600; 2018-10-01: 0; 2018-11-01: 0 | -4600 | Actual
| Galvanization ton | 1236 | 1500 | 1854000 | 1480000 | 1871500 | 1771500 | 4.446% | -1336445 | 0 | 0 | -51529.5958 | -51529.5958 |  | -65000 | -65000 | -65000 | -50000 |  |  |  | -1684504.1915 | Plan | 186995.8085
[9 empty] | -1336445 | 0 |  |  | -144295 | -27337.6 | -37262.5 | -4200 | -41925 | -42475 | 0 | -71062.5 |  | -1705002.6 | Actual
| Third Party Inspection visits | 30 | 2500 | 75000 | 75000 | 100000 | 125000 | 0.2253% | -52500 | -4500 | -4000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 |  |  |  |  | -97000 | Plan | 3000
[9 empty] | -58372.35 | -4040 | -3105 | -2822 | -5963 | -17262 | -2038 | -957.5 | -8931.25 | -22212.2 | 0 | -455 |  | -126158.3 | Actual
| Survey months | 10 | 15000 | 150000 | 150000 | 150000 | 105000 | 0.4507% | 2017-12-17: -78000; 2018-01-01: -20000; 2018-02-01: -10000; 2018-03-01: -10000; 2018-04-01: -10000; 2018-05-01: -10000; 2018-06-01: -10000 | -148000 | Plan | 2000
[9 empty] | 2017-12-17: -64244.42; 2018-01-01: -18367; 2018-07-01: -13784.61; 2018-09-01: 0; 2018-10-01: 0; 2018-11-01: 0 | -96396.03 | Actual
| Others- Handrails items | 1 | 450000 | 450000 | 450000 | 450000 | 508013 | 1.352% | 2017-12-17: 0; 2018-01-01: 0; 2018-04-01: 0; 2018-05-01: 0; 2018-06-01: 0 | 0 | Plan | 450000
[9 empty] | 2017-12-17: 0; 2018-09-01: 0; 2018-10-01: 0; 2018-11-01: 0 | 0 | Actual
| Space frame& space frame fire proof | 1 | 15000000 | 15000000 | 15530395 | 14570000 | 14420000 | 46.66% | -2152484.7095 | -1241751.5291 | -1241751.5291 | -1241751.5291 | -1241751.5291 | -1241751.5291 | -1241751.5291 | -1241751.5291 | -1241751.5291 | -1241751.5291 | -1241751.5291 |  |  | -14570000 | Plan | 0
[9 empty] | -2152484.7095 | -129186.56 | -232307.554 | -52441.5 | -463551 | -1637697 | -657305.68 | -37118.03 | -102469 | -395533.38 | -2985457.49 | -3183299.67 |  | -12028851.5735 | Actual
| Space frame- fire proofing | 1 | 0 | 4700000 | 0 | 0 | 0 | 0% | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | Plan | 0
[9 empty] | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  | 0 | Actual
| Total Plan |  |  | 2355025 | 18624635 | 18144500 | 17891513 | 55.96% | -3878123.7095 | -1437878.4724 | -1367378.4724 | -1385917.8382 | -1385917.8382 | -1334388.2424 | -1399388.2424 | -1419388.2424 | -1659796.6624 | -1368388.2424 | -1241751.5291 | 0 | 0 | -17878317.4915 | Plan | 266182.5085
| Total Actual | [7 empty] | -3870135.7595 | -152860.23 | -326356.654 | -58430.5 | -629809 | -1687482.6 | -696606.18 | -56060.14 | -174745.25 | -460220.58 | -2985457.49 | -3247815.16 | 0 | -14345979.5435 | Actual
| Accum Total Plan |  |  | 2355025 | 18624635 | 18144500 | 17891513 | 55.96% | -3878123.7095 | -5308014.2319 | -6675392.7043 | -8061310.5424 | -9447228.3806 | -10781616.623 | -12181004.8653 | -13600393.1077 | -15260189.7701 | -16628578.0125 | -17870329.5415 | -17870329.5415 | -17870329.5415 | -17870329.5415 | Plan | -3524349.998
| Accum Total Actual | [7 empty] | -3870135.7595 | -4022995.9895 | -4349352.6435 | -4407783.1435 | -5037592.1435 | -6725074.7435 | -7421680.9235 | -7477741.0635 | -7652486.3135 | -8112706.8935 | -11098164.3835 | -14345979.5435 | -14345979.5435 | -14345979.5435 | Actual
4 | Equipment, Tools, and trans
| Tools | 1 | 50000 | 50000 | 50000 | 50000 | 20000 | 0.1502% | 2017-12-17: -8000; 2018-01-01: -8000; 2018-02-01: -8000; 2018-03-01: -8000; 2018-04-01: -8000; 2018-05-01: -8000 | -48000 |  | 2000
[9 empty] | 2017-12-17: -9021.34; 2018-09-01: 0; 2018-10-01: 0; 2018-11-01: -4563.04 | -4563.04
| Transportation Trip | 125 | 1200 | 150000 | 150000 | 150000 | 120000 | 0.4507% | 2017-12-17: -50000; 2018-01-01: -15000; 2018-02-01: -15000; 2018-03-01: -15000; 2018-04-01: -15000; 2018-05-01: -15000; 2018-06-01: -15000 | -140000 |  | 10000
[9 empty] | -45020 | -2950 | -725 | -5530 | -5380 | -8064 | -12335 | -2825 | -6250 | -7400 | -2050 | -10200 |  | -108729
| Total Plan |  |  | 200000 | 200000 | 200000 | 140000 | 0.6009% | -58000 | -23000 | -23000 | -23000 | -23000 | -23000 | -15000 | 0 | 0 | 0 | 0 | 0 | 0 | -188000 | Plan
| Total Actual | [7 empty] | -54041.34 | -2950 | -725 | -5530 | -5380 | -8064 | -12335 | -2825 | -6250 | -7400 | -2050 | -14763.04 | 0 | -122313.38 | Actual
| Accum Total Plan |  |  | 200000 | 200000 | 200000 | 140000 | 0.6009% | -58000 | -77041.34 | -100041.34 | -123041.34 | -146041.34 | -169041.34 | -184041.34 | -184041.34 | -184041.34 | -184041.34 | -184041.34 | -184041.34 | -184041.34 | -184041.34 | Plan | -61727.96
| Accum Total Actual | [7 empty] | -54041.34 | -56991.34 | -57716.34 | -63246.34 | -68626.34 | -76690.34 | -89025.34 | -91850.34 | -98100.34 | -105500.34 | -107550.34 | -122313.38 | -122313.38 | -122313.38 | Actual
5 | Others
| Contingency | 1 | 50000 | 50000 | 320000 | 320000 | 443000 | 0.9614% | -320000 | -163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -10163.1983 | -431958.38 |  | -111958.38
[9 empty] | -319020.81 | -24878.18 | -300 | -16766.9 | -2500 | -46491.7 | -9122.54 | -732.76 | -38374.34 | -35519.06 | -220 | -44051.19 |  | -537977.48
| Vehicle expense/allowance | 1 | 250000 | 250000 | 250000 | 250000 | 300000 | 0.7511% | -220000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 | -6000 |  |  |  |  | -268000 |  | -18000
[9 empty] | -216805.75 | -6658 | -6047 | -6805 | -8850 | -7755 | -5506.5 | -9385 | -8134 | -7159.5 | -10154.25 | -7386 |  | -300646
| Site mobilization | 1 | 50000 | 50000 | 50000 | 50000 | 5000 | 0.1502% | 2017-12-17: -10000 | -10000 |  | 40000
[9 empty] | 2017-12-17: -3298; 2018-09-01: 0; 2018-11-01: 0 | -3298
| Other | 1 | 50000 | 50000 | 191000 | 250000 | 305000 | 0.5738% | -191000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 | -5000 |  | -246000 |  | 4000
[9 empty] | -197468 | -23720 | -4540.37 | -21745 | -7498 | -12391 | -1701 | -11853 | -7502.25 | -4535.5 | -3127 | -9859 |  | -305940.12
| Management provision |  | 0 | 0 | 1200000 | 1200000 | 400000 | 3.605% | 2017-12-17: -600000; 2018-04-01: 0; 2018-05-01: 0; 2018-06-01: 0; 2018-09-01: -600000 | -1200000 |  | 0
[9 empty] | 2017-12-17: 0; 2018-09-01: 0; 2018-10-01: 0 | 0
| Cost of car shed items |  | 0 | 0 | 950000 | 0 | 0 | 2.854% | 2017-12-17: 0 | 0 |  | omitted
[9 empty] | 2017-12-17: 0; 2018-09-01: 0; 2018-10-01: 0 | 0
| Total Plan |  |  | 400000 | 2961000 | 2070000 | 1453000 | 8.896% | -1341000 | -11163.1983 | -21163.1983 | -21163.1983 | -21163.1983 | -21163.1983 | -21163.1983 | -21163.1983 | -21163.1983 | -615163.1983 | -15163.1983 | -15163.1983 | -10163.1983 | -2155958.38 | Plan | -85958.38
| Total Actual | [7 empty] | -736592.56 | -55256.18 | -10887.37 | -45316.9 | -18848 | -66637.7 | -16330.04 | -21970.76 | -54010.59 | -47214.06 | -13501.25 | -61296.19 | 0 | -1147861.6 | Actual
| Accum Total Plan |  |  | 400000 | 2961000 | 2070000 | 1453000 | 8.896% | -1341000 | -1352163.1983 | -1373326.3967 | -1394489.595 | -1415652.7933 | -1436815.9917 | -1457979.19 | -1479142.3883 | -1500305.5867 | -2115468.785 | -2130631.9833 | -2145795.1817 | -2155958.38 | -2155958.38 | Plan | -1008096.78
| Accum Total Actual | [7 empty] | -736592.56 | -791848.74 | -802736.11 | -848053.01 | -866901.01 | -933538.71 | -949868.75 | -971839.51 | -1025850.1 | -1073064.16 | -1086565.41 | -1147861.6 | -1147861.6 | -1147861.6 | Actual
Summation
| Total Plan |  |  | 9962125 | 33284959 | 34342464 | 33306177 | 100% | -12691897.7095 | -1717599.8356 | -1651255.1611 | -1823649.4933 | -1675216.577 | -1666549.1706 | -1649068.3409 | -1654068.3409 | -2330054.255 | -2111645.835 | -1449914.7274 | -202163.1983 | -42163.1983 | -30665245.843 | Plan
| Total Actual |  |  | -9962125 | -33284959 | -34342464 | -33306177 |  | -14476821.6642 | -464758.15 | -636066.364 | -227982.2 | -1002543.7 | -2079652 | -1338133.11 | -466468.93 | -741229.8 | -982193.99 | -3339083.56 | -3456805.66 | 0 | -29211739.1282 | Actual
| Accum Total Plan (PV) | [7 empty] | -12691897.7095 | -14409497.5451 | -16060752.7062 | -17884402.1995 | -19559618.7765 | -21226167.9471 | -22875236.288 | -24529304.6289 | -26859358.8839 | -28971004.7189 | -30420919.4463 | -30623082.6446 | -30665245.843 | -30665245.843 | Plan | -1453506.7148
| Accum Total Actual (AC) | [7 empty] | -14476821.6642 | -14941579.8142 | -15577646.1782 | -15805628.3782 | -16808172.0782 | -18887824.0782 | -20225957.1882 | -20692426.1182 | -21433655.9182 | -22415849.9082 | -25754933.4682 | -29211739.1282 | 0 | -29211739.1282 | Actual
Cash IN
| Payment Application | [7 empty] | 2017-12-17: 13839459
| Payment Certificate | [7 empty] | 2017-12-17: 9199889.8845
| Collection | [7 empty] | 2017-12-17: 4274976
| Payment Application / Actual Cost | [7 empty] | 2017-12-17: 95.6%
[9 empty] | 63.55% | pay of cost | make forecast per month for how many pay certf you will make each month/cost
[9 empty] | #DIV/0! | pay to project price
the cost to be broken down on the time line, the data to be entered in the start of the project based on the project schedule
Data to be updated on monthly bases based on the actual monthly expenditures
Note on AE2: Author: AAE letter no 110, 6jan18
Note on AE3: Author: AAE letter no 249, 26jul18
Note on H4: Author: data are taken manually from the budget revised data made by PM or by senior management
Note on AC4: Author: AAE lett no 099, 24dec17.
Note on J7: Author: cost is splited on the timeline based on the project schedule
Note on J8: Author: data are taken from the cost account dept on monthly bases
Note on AJ15: Author: after meeting with QC manager to reduce the cost of the qc on the project budget
Note on AC30: Author: 40 ton additional material (contingency)
Note on AE30: Author: canyoning platform
Note on E31: Author: saving in your budget estiamted 17K m2 but the real is 6k m2
Note on AE41: Author: 10% for studs
Note on J50: Author: 28,206 of this 80,041 this cost is located wrongly for survey of arab land, to be modified with oaccountants
Note on W53: Author: 140K paid to RAV 240K committ to RAV but I will give only 150K 600K to Mulhen
Note on J66: Author: 3rd party- advance payment AYZ
Note on L66: Author: check the details
Note on B85: Author: other
Note on J111: Author: from cash in sheet