## 2.1
PROJECT MANAGEMENT PLAN
Scope Management Plan
Collect Requirements (how the requirements will be collected categorized)
1 | The basic requirements will be collected from the project contract/specifications.
2 | For senior management of "Your Organization" and "Customer", requirements will be collected by interview (one-one meeting).
3 | For department heads at "Your Organization" and "Customer", requirements will be collected by group meeting for each department.
4 | For the remaining stakeholders, the requirements will be collected by mail.
Scope Statement (how the project scope statement will be developed)
1 | Based on the project agreements (contract) and highlighted drawings attached with the contract, the project scope statement will be created.
2 | The project scope statement should include The project In-scope and Out-of-scope In each part of The project including the marked drawing.
3 | A letter should be send to The client In The In The planning stage that any items not mentioned as In-scope In The highlighted drawings will be considered as Out-of-Scope.
4 | The technical and estimation depts to study all the project drawings/specs in details and communicate with client by official FRIs for any unclear or hidden or incomplete data or information.
5 | The scope statement will be created as first draft by The project coordinator based on The requirements documents, then will be reviewed and fine tuned by project manager, then will be reviewed by senior management.
6 | After clearing all The scope of work, A formal written communication (letter) should be sent to client highlighting all The agreed points by attaching to The letter The project scope statement.
WBS (how WBS will be developed)
1 | The WBS will be developed though meeting/s between the PM and the project team.
2 | The WBS template (excel sheet will be used).
Validate Scope (how the deliverables will be validated)
1 | The inspection request will be sent to Client as per IR request (form is available with QC team).
2 | If inspection is accepted by client/consultant, they will sign/stamp on the IR, if not accepted and have comments, the comments will be mentioned in the IR for rectifications, then revised IR will be submitted again.
3 | Material Inspection- Production inspection- Delivery inspection- NDT- Painting inspection- Final Product. all of them will have the following procedure:
Control Scope (how the scope will be controlled and how the scope baseline will be maintained)
1 | The scope may be leaked from the following areas: contract awareness- engineering- production- installation.
2 | In the planning stage the PM will send the project scope highlighted drawings to all project team (departments) to be understood by all project depts. Explain clearly the project scope as per the contract and scope statement& highlighted drawings if any.
3 | Hold a monthly meeting with title scope control meeting to ensure that no excluded scope will be implemented without change request.
Schedule Management Plan
Collect Requirements (how the requirements will be collected categorized)
The basic requirements will be collected from the project contract/specifications.
Schedule Methodology (such as critical path, critical chain, or some other methodology)
The schedule methodology will be the critical path method.
Scheduling Tools (Tools can include scheduling software, reporting software, earned value software)
The planning team will use P6 as a scheduling tools, P6 will be used in the planning and reporting purpose.
Level of Accuracy (Describe the level of accuracy needed for estimates)
1 | The clear Steel works such as the Karting Roof building (no interfere with concrete or other works- design completed) will be estimated with high accuracy will be within limits of -/+10% times estimates.
2 | The steel works that interfere with other concrete works/design is not complete/ subjected to variation works, the estimates will be subjected to variance of +25% of time estimates.
3 | The other categories of works such as space frame and awning will be using 'rolling wave technique' and limits of high level estimates will be with -/+50% and will be refines after assigning the subcontract specialist.
Units of Measure (Indicate whether duration estimates will be in days, weeks, months,...).
The units of measure will be in Days.
Schedule Reports and Formats
1 | Daily progress reports in excel format (to be prepared by factory/site engineer indicating the daily work at factory/site).
2 | Weekly progress report will be issued by P6 in PDF formats indicating the progress status and delayed items. So that the PM can monitor and take action in the delayed packages.
3 | The planning dept to submit recovery plan by P6 in PDF formats in order to recover the delayed packages.
How Activities will be estimated and sequenced
Define Activities and Estimate Activates Duration and Resources:
1 | The activity list will be created by the project manager and project team.
2 | The activity duration and resources will be estimated using the 3 point estimate or parametric tech.
3 | The estimates will developed by the help of the contract team and functional managers of each package.
How Schedule will be Developed
1 | The activity list, activity durations, and activity resources to be developed to overall schedule made on excel sheet created by the project manager.
2 | Then the excel sheet schedule to be handed to the planner to develop the schedule via P6.
How Schedule Baseline will be Controlled
1 | The project planner to update the schedule baseline on weekly basis on Saturdays.
2 | The project manager to have meeting on weekly basis on Sundays with the project team and the subcontractors to discus the project status, the schedule update will be one of the main meeting agenda to discuss the delay and take commitments from the project team and subcontractors for the recovery plans.
3 | The agreed recovery dates to be recorded by the project coordinator (or clever document controller), to be send officially to the related teams/departments/companies. |  | Project Manager Name |  |  |  | Sponsor Name
4 | The project coordinator/engineer to follow up the agreed action to ensure they are taken in real and recovery plans are implemented.
Variance Threshold
Based on the schedule control which will be on weekly bases, any variance of the activities from the baseline should be control, threshold to be followed as following plan:
1 | If the activity is on track therefore no action to be taken,
2 | If the activity/package is delayed up to 1% of the project schedule baseline, the PM to send mail to the delayed party notifying the delay and asking for corrective action+ to be highlighted in the weekly meeting.
3 | If the activity/package is delayed up to 2% of the project schedule baseline, the PM to send official letter to the delayed party notifying the delay and asking for corrective action.
4 | If the activity/package is delayed more than 3% of the project schedule baseline, the PM to send official warning letter to the delayed party warning with taking corrective and hold the due payment (or replacing the team if internal team).
5 | If no action taken or only slow and poor action was taken, the PM to send contractual letter notifying the delayed party that he will hire another subcontractor.
Cost Management Plan
Units of Measure
The units of measure will be in "Qar"
Reports and Formats
You will receive a weekly report from the cost control of the project budget and manpower/material consumption.
You will issue a monthly report to the management of the project cost control using the earned value analysis.
How Cost will be estimated and aggregated
1 | Using the activity list& project duration and resources, the cost will be estimated using the parametric estimating.
2 | Based on the risk register, the contingency reserves will be added to the project costs.
3 | Based on the meeting with the senior management, the management reserve will be added.
How the baseline will be Developed
Based on the final cost estimates, the PM will compare the output with the project/contract budget, it aligned is it ok.
In case the estimates is bigger than the contract budget, the PM to revisit the estimates and work to reduce the costs by re estimating the value, and by removing some risks, if still higher, the PM to meet with the senior management and inform that the estimates the contract budget can not obtain, and he should prepare some alternative analysis such as reducing the scope-quality.
How Cost Baseline will be Controlled
1 | The cost controller to update the actual costs on weekly basis on Saturdays.
2 | The project manager to have meeting on weekly basis on Sundays with the project team to discus the project status, controlling the cost will be one of the main meeting agenda to discuss how to reduce the manhours/equipment cost without affecting the progress. then take commitments from the project team for the recovery plans.
3 | The agreed actions to be recorded by the project coordinator (or clever document controller), to be send officially to the related teams/departments/companies.
4 | The project coordinator/engineer to follow up the agreed action to ensure they are taken in real and recovery plans are implemented.
Variance Threshold
Based on the cost control which will be on weekly bases, any variance of the activities from the baseline should be control, threshold to be followed as following plan:
1 | If the cost is on track therefore no action to be taken.
2 | If the cost is overbudget up to 1%, the PM to send mail to the caused department party notifying the issue and asking for corrective action+ to be highlighted in the weekly meeting.
3 | If the cost is overbudget up to 2%, the PM to send official letter to the caused party notifying the issue and asking for corrective action.
4 | If the cost is overbudget up to 3%, the PM to send official warning letter to the cause party warning with taking corrective and hold the due payment (or replacing the team if internal team).
5 | If no action taken or only slow and poor action was taken, the PM to send contractual letter notifying the delayed party that he will hire another subcontractor.
Quality Management Plan
Quality Plan
1 | Quality department to prepare the Company prequalification
2 | Quality department to prepare the method statements
3 | Quality department to prepare the inspection test plan ITP
4 | Quality department to prepare internal plan for inspecting the products of the project prior submitting inspection request to client
5 | Quality department to prepare a monthly plan for internal audit on the processes of the project.
6 | Quality manager with project manager to meet monthly to determine what will be used to continuously improve quality for the product and processes.
7 | Quality department to initiate and implement the "clearance" system to be used as authorization system between project phase gates.
Resource Management Plan
R-A-C-I
| Contract |  | Contract / Agreement | Approved BOQ | Initial Budget | IFC Drawings
| contract Manager |  | R | A | A | A
| contract Engineer |  | R | R | R | R
| PM |  | I | I | I | I
| operation manager |  | I | I | I | I
| Engineering |  | Review IFC | Raise RFI | Solve issues | Submit shop dwg | Attend tech meetings | Solve sever issues
| engineering manager |  | A | A | A | A | A | R
| engineering coordinator |  | R | R | R | R | R | R
| designer |  | C | C | C | C | C | C
| operation manager |  | I | I | I | I | I | I
| PM |  | A | I | I | I | I | I
| Construction |  | Site plan | Erection work | Equipment | Site meeting
| site engineer |  | R | R | R | R
| site manager |  | A | A | A | R
Training Plan
1 | In the beginning of the project, the PM to evaluate his team in regard to the required skills they should fulfill to complete the project activities.
2 | In the middle of the project, the PM to re-evaluate the team competences and determine the required skills they should have to complete the project activities.
3 | The priority for the training will be for the in-house training.
4 | The priority for the training team is for the direct works, then the indirect works.
Team Charter
1 | Team members
| 1 | Project manager |  | Name
| 2 | Engineering coordinator |  | Name
| 3 | Fabrication engineer |  | Name
| 4 | Construction manager |  | Name
| 5 | Construction engineer |  | Name
| 6 | Quality control engineer |  | Name
| 7 | Quantity survey |  | Name
2 | Driver
|  | Project Manager |  | Mohamed Naser
3 | Team Goal
Finish the project within budget and within the time frame.
Create a role model for this project to be used in the organization.
4 | Expectation
| 1 | Being open, and support each other.
| 2 | Good communication for good collaboration.
| 3 | Finish the work with required quality.
| 4 | Finish the work as quickly as possible.
| 5 | Deal with each other positively and make the required in good manners.
| 6 | When someone has problems, we should all help to solve it, business or personal.
| 7 | If someone has shortage/defect, the other should help to support and strengthen it.
5 | Team Values
| 1 | Be helpful and share the knowledge. |  |  | 10 | Maintain a cooperation behavior.
| 2 | Deal with lately and trust. |  |  | 11 | Don't say words like stones.
| 3 | Be open and don’t hide issues. |  |  | 12 | Be direct in dealing with conflict.
| 4 | Focus on project interest not your own interest. |  |  | 13 | Act impartially without favoritism, bribery.
| 5 | Only accept work that you can do. |  |  | 14 | Look for conflicts of interest and disclose them.
| 6 | Acknowledge your own errors. |  |  | 15 | Don’t discriminate against others.
| 7 | Fight to achieve your commitments |  |  | 16 | Don’t use your position for personal gain.
| 8 | Uphold laws. |  |  | 17 | Try to understand the truth.
| 9 | Respect the culture of each other. |  |  | 18 | Don’t deceive others.
| 10 | Maintain a cooperation behavior. |  |  | 19 | Create an environment where other tell the truth.
| 11 | Don't say words like stones. |  |  | 20 | Do not make fun of others
6 | Obstacles
Work pressure make people nervous
One of the team is negative or aggressive
Keep things hidden
One of the team is harmful to others
One of the team insists on his ideas
7 | Energy Sources
Every Thursday the team to make one meeting to learn something new.
Having fun
Every week the team to take breakfast together
Playing football together
Use the challenge to achieve targets with time frame limits.
Make man of the week competition
The team to set in one room (colocation)
8 | Conflict Management
The project emphasizes early, efficient, and collaborative conflict management across the organization. This informal template serves to encourage timely and consistent conversations that normalize the occurrence of conflict and seek to solve it at the local level.
In case of any conflict between team members, to be solved personally among these team based on the Team Charter (click here to see the "Team Charter").
If problem is not solved, the PM to be involved to solve the problems based on the objective of the project.
Communications Management Plan
Document Communication Matrix
Sr | Doc |  | Doc Type | Via | From | To | When | How often
1 | "Your Organization" quotation |  | Report | Mail | Contract | Project | Initiating | Once
2 | LOI / LOA |  | Letter | Mail | Contract | Project | Initiating | Once
3 | Contract / Agreement |  | Contract | Memo | Contract | Project | Initiating | Once
4 | Approved BOQ |  | Contract | Memo | Contract | Project | Initiating | Once
5 | Initial Budget |  | Contract | Memo | Contract | Project | Initiating | Once
6 | IFC Drawings |  | Contract | Memo | Contract | Project | Initiating | Once
7 | Project Specification |  | Contract | Memo | Contract | Project | Initiating | Once
8 | Scope Matrix |  | Contract | Memo | Contract | Project | Initiating | Once
9 | Provision |  | Contract | Memo | Contract | Project | Initiating | Once
10 | Shop dwg log |  | Report | Mail | Engineering | Project | Execution | Weekly
11 | PRs log |  | Report | Mail | Engineering | Project | Execution | Weekly
12 | RFI log |  | Report | Mail | Engineering | Project | Execution | Weekly
13 | Fab dwg log |  | Report | Mail | Engineering | Project | Execution | Weekly
14 | Eng manhours |  | Report | Mail | Engineering | Project | Execution | Monthly
15 | PR-LPO log |  | Report | Mail | Procurement | Project | Execution | Weekly
16 | Fab progress |  | Report | Mail | Production | Project | Execution | Weekly
17 | Fab manhours |  | Report | Mail | Production | Project | Execution | Monthly
18 | Quality plan |  | Report | Mail | QC | Project | Planning | Once
19 | Fab Method statement |  | Report | Mail | QC | Project | Execution | Once
20 | ITP |  | Report | Mail | QC | Project | Execution | Once
21 | Inspection log |  | Report | Mail | QC | Project | Execution | Monthly
22 | NCR log |  | Report | Mail | QC | Project | Execution | Monthly
23 | Inst method statement |  | Report | Mail | Construction | Project | Execution | Once
24 | Progress report |  | Report | Mail | Construction | Project | Execution | Weekly
25 | Const manhours |  | Report | Mail | Construction | Project | Execution | Monthly
26 | IFC Drawings |  | Report | Memo | Project | All | Initiating | Once
27 | Project Specification |  | Report | Memo | Project | All | Initiating | Once
28 | Baseline schedule |  | Report | Memo | Project | All | Initiating | Once
29 | Summary report |  | Report | Meeting/mail | Project | Org Management | All phases | Monthly
30 | Summary report |  | Report | Meeting/mail | Project | Client | All phases | Monthly
31 | Technical meetings |  | MOM | Mail | Engineering | Project | Any phase | Any time
32 | Construction meetings |  | MOM | Mail | Construction | Project | Any phase | Any time
33 | Procurement meetings |  | MOM | Mail | Procurement | Project | Any phase | Any time
Meeting Matrix
Sr | Meeting |  | Type | With | When |  | Content
1 | Project status meeting |  | Internal | Sen Management | Monthly ( Last Sunday) |  | Progress- Plan- Risk
2 | Project status meeting |  | Internal | Project team | Weekly (Thursday) |  | Progress- Plan- Risk
3 | Project status meeting |  | External | Client | Weekly (Sunday) |  | Progress- Plan- Risk
4 | Other (Urgent only) |  | Int-or-Ext | Team-or-client | When requested |  | Urgent issues
Mail Communication Matrix
Sr | Mail Topic | Type | From | To | CC |  | Mail Subject
1 | Technical | Internal | Engineering coordinator | Team leader | PM- team leader manager |  | Project Number- Project Name-Technical- Mail Title (mail title should be to the core point of the mail)
|  | External | Engineering coordinator | Client engineering coordinator | PM- client engineering manager
2 | Contractual | Internal | Contract engineer | PM | Contract manager |  | Project Number- Project Name-Contractual- Mail Title (mail title should be to the core point of the mail)
|  | External | Contract engineer | PM | Contract manager
|  |  | PM | Client contract manager | Contract manager-contract engineer
3 | Construction | Internal | Construction engineer | Team leader | PM- Construction manager |  | Project Number- Project Name-Construction- Mail Title (mail title should be to the core point of the mail)
|  | External | Construction engineer | Client construction engineer | PM- construction manager- client construction manager
4 | Commercial | Internal | Quantity survey | PM | Account manager |  | Project Number- Project Name- Commercial- Mail Title (mail title should be to the core point of the mail)
|  |  | Cost control | PM | Account manager
|  | External | PM | Client cost control | Quantity survey- cost control- account manager- client account manager
|  |  |  | Client account responsible | Quantity survey- cost control- account manager- client account manager
5 | Quality | Internal | Quality engineer | PM | Quality manager |  | Project Number- Project Name- QC- Mail Title (mail title should be to the core point of the mail)
|  | External | Quality engineer | Client quality engineer | PM- quality manager- client quality manager
6 | Additional works | Internal& external | Project team | client- project team | PM |  | Project Number- Project name- Scope- Mail title (mail title should be to the core point of the mail)
7 | Site Conditions | Internal& external | Project team | client- project team | PM |  | Project Number- Project name- Site issues- Mail title (mail title should be to the core point of the mail)
Mail Archiving (this part is mandatory for the project team to follow- for other stakeholders is it optional).
| Folder Number | Folder Name | Content
| 1 | Dow it Now | Work that can be finished in 2 minutes of less. After finishing, move this mail to "Reference" or to "Archive".
| 2 | Open Issues | Work that can be finished in more than 2 minutes. After finishing, move this mail to "Reference" or to "Archive".
| 3 | Delegate | Work you already delegated to one of your team. After finishing, move this mail to "Reference" or to "Archive".
| 4 | Reference | Important mails such as letters- variations- site issues- important decisions-…
| 5 | Archive | The mails you have already read and not important of not required to be in "Reference".
| 6 | Not Needed | Mails are not related to the core of the project such as IT mails.
Risk Management Plan
The project will focus on implementing the risk management heavily using the what-if analysis through the project phases
Important definitions regarding the risk management:
| Risk Category: | In this project, the risks will be categorized by project phase (design- engineering- procurement- fabrication- delivery- erection- inspection- handing over).
| Risk Types: | Pure Risk: when the risk makes negative impact.
Business Risk: when the risk makes negative or positive impact.
| Probability: | Ranked from 1 (very low probability) to 5 (very near to happen).
| Impact: | Ranked from 1 (very low impact on the project) to 5 (impact the project catastrophically).
| Risk Owner: | The risk owner will be set based on each phase, for ex. The risks fall into the design phases will be taken care by the design manager and so on.
| Control Risk: | A weekly and monthly meeting will be hold and the risk will be addressed and controlled (look meeting matrix) (click here to see "Meeting Communication Matrix")
Impact Probability Matrix:
Impact
| Schedule | 12 | Time impact | VL cost impact | L cost impact | M cost impact | H cost impact | VH cost impact
|  |  |  | 1% | 2% | 3% | 5% | 10%
|  |  | months | 0.12 | 0.24 | 0.36 | 0.6 | 1.2
| Budget | 10000000 | Cost impact | VL cost impact | L cost impact | M cost impact | H cost impact | VH cost impact
|  | Qar |  | 0.1% | 0.2% | 1% | 2% | 5%
|  |  | qar | 10000 | 20000 | 100000 | 200000 | 500000
|  |  |  | 1 | 2 | 3 | 4 | 5
| Probability | VL probability <10% | 1 | 1 | 2 | 3 | 4 | 5
|  | L probability >10% & < 20% | 2 | 2 | 4 | 6 | 8 | 10
|  | M probability >20% & <40% | 3 | 3 | 6 | 9 | 12 | 15
|  | H probability >40% & <80% | 4 | 4 | 8 | 12 | 16 | 20
|  | VH probability >80% | 5 | 5 | 10 | 15 | 20 | 25
Procurement Management Plan
The procurement plan will be established based on the organization policy in this regard.
Stakeholder Management Plan | [8 empty] | 6000
Will be handled later.
Change Management Plan
The PM to put a procedure that any requested change (out of scope) as follows:
1 | Any change request received from client- internally- or third part should be send to PM with clear details about the change such as related BOQ and drawings.
2 | The PM review and send the change to the quantity survey team to study inform the PM with the impact time and cost.
3 | The PM will decide if the change within time and cost of the project he will give instruction to proceed, if the change has impact on the time of cost, it will be addressed officially to the client requesting for variation approval (instruction to proceed).
4 | The team will proceed with the work once confirmation obtained from client in p.3.
5 | The quantity survey team to prepare variation claim with the impact cost and time to be submitted to client.
Improvement Management Plan
1 | The project will follow a monthly meeting with the quality manager and project team to discuss the project flow, reports, and overall processes.
2 | The project manager to solve immediately the raised problems in the project.
3 | The project manager to monitor the repeated problems, find the root cause, and suggest preventive actions.
4 | The project to follow 5-S technique for environment arrangement.
5 | The project to follow Kaizen technique by implementing small changes on repeated attitude.
Configuration Management Plan
Will be handled later.
Approvals
|  |  | Project Manager Name |  |  |  | Sponsor Name
|  |  | Project Manager Signature |  |  |  | Sponsor Signature
|  |  | Date |  |  |  | Date