## 4.1
Company Name |  | Project No. | Update Date
Project Name |  |  |  | CPI | 0.78624 | SPI | 0.75
Cash out |  |  |  | Cash In |  |  | Progress
Budget | BAC | -33306177 |  | Project Value | 43710054 |  | Plan | 98%
Planned Cost | PV | -30623082.6446 |  | Adv Payment | 4204461.15 |  | Actual | 75%
Actual Cost | AC | -29211739.1282 |  | Invoiced | 34732811.5173
Earned Vlaue | EV | -22967311.9835 |  | Certified | 33603179.9107
Estimate At Complete | EAC | -30665245.843 |  | Cashed | 25793741.1463
Estimate To Complete | ETC | -1453506.7148
Budget Elements | Plan | Act |  | Budget | Plan | Actual | %
Production, hr/ton | 70 | 60 |  | Manpower | -6961007.9799 | -7913340.29 | 113.7%
Engineering, hr/ton | 3 | 60 |  | Material | -6298988.8815 | -5682244.3147 | 90.21%
Projects, hr/ton | 7 | 12 |  | Subcontractor | -17870329.5415 | -14345979.5435 | 80.28%
Construction, hr/ton | 60 | 150 |  | Equipment | -184041.34 | -122313.38 | 66.46%
QC, hr/ton | 4 | 7 |  | Others | -2155958.38 | -1147861.6 | 53.24%